## Project Plan
Scrum Leader Sebastian Vasquez
| Task Name | Priority | Estimated Hours (Effort Points) | Planned Start Date | Planned End Date | Milestone 1 | Assigned | Free Time
[9 empty] | Sebastian | Rami | Dante | Angel | Emily | Jacob | Rifat | all
| Low Level View favorite Medication Lost | 1 | 7 |  | 2022-03-23 |  | Rami
Low Levels - Sebastian | Low Level Add favorite medication | 2 | 7 |  | 2022-03-23
| LL Edit Weight Goal | 3 | 5 |  | 2022-03-23 |  | Sebastian | 2022-03-14 | 5 | 8 | 4 | 1 | 3 | 4 | 6 | 31
Code- Emily | LL Search Food Item | 4 | 5 |  | 2022-03-23 |  | Sebastian | 2022-03-15 | 5 | 8 | 4 | 5 | 4 | 4 | 8 | 38
| Edit Weight Goal Code | 5 | 6 |  | 2022-03-23 |  | Sebastian | 2022-03-16 | 6 | 8 | 6 | 2 | 6 | 4 | 6 | 38
| Search Food Item Code | 6 | 6 |  | 2022-03-23 |  | Sebastian | 2022-03-17 | 8 | 8 | 4 | 5 | 4 | 4 | 3 | 36
[8 empty] | 2022-03-18 | 5 | 8 | 6 | 8 | 3 | 4 | 3 | 37
| Program add Favorite Medication | 7 | 3 |  | 2022-03-23 |  | Rami | 2022-03-19 | 3 | 8 | 4 | 8 | 4 | 6 | 2 | 35
| Program view Favorite Medication | 8 | 5 |  | 2022-03-23 |  | Rami | 2022-03-20 | 4 | 8 | 6 | 8 | 5 | 4 | 5 | 40
| Create Records LL | 9 | 10 |  | 2022-03-23 |  | Angel | 2022-03-21 | 5 | 8 | 4 | 4 | 4 | 4 | 4 | 33
| Frontend Code Create Records |  | 7 |  | 2022-03-23 |  | Angel | 2022-03-22 | 5 | 8 | 4 | 5 | 4 | 4 | 5 | 35
| Backend Code Create Records | 10 | 7 |  | 2022-03-23 |  | Angel | 2022-03-23 | 6 | 8 | 4 | 2 | 6 | 4 | 4 | 34
[8 empty] | Totals | 52 | 80 | 46 | 48 | 43 | 42 | 46 | 357
| Search Health Locator LL Draft | 11 | 5 |  | 2022-03-23 |  | Jacob
| View Search Locator LL Draft | 12 | 5 |  | 2022-03-23 |  | Jacob
| Code Search Health Locator Backend | 13 | 6 |  | 2022-03-23 |  | Jacob
| Code Delete Favorite |  | 3 |  |  |  | Rami
| Low Level Delete Favorite |  | 5 |  |  |  | Rami
| Code View Medication |  | 4 |  |  |  | Rami
| Low Level View Medication |  | 7 |  |  |  | Rami
| Test favorite Medication |  | 7 |  |  |  | Rami
| Front End Favorite Medication |  | 6 |  |  |  | Rami
| LL view Reminder | 14 | 7 |  | 2022-03-23 |  | Dante
| LL Delete Reminder | 15 | 7 |  | 2022-03-23 |  | Dante
| LL Edit Reminder | 19 | 7 |  | 2022-03-23 |  | Dante
| Backend Code view reminder | 16 | 8 |  | 2022-03-23 |  | Dante
| LL Favorite News Article | 17 | 8 |  | 2022-03-23 |  | Rifat
| Favorite News Article Code | 18 | 9 |  | 2022-03-24 |  | Rifat
| LL View Details Diet Recommendation | 19 | 8 |  | 2022-03-23 |  | Emily
| Code View Details Diet Recommendation | 20 | 8 |  | 2022-03-23 |  | Emily
|  |  | 6 |  |  |  | Sebastian
155
3.6905