## Project Plan
Scrum Leader Sebastian Vasquez
| Task Name | Priority | Estimated Hours (Effort Points) | Planned Start Date | Planned End Date | Milestone 1 | Assigned | Free Time
[9 empty] | Sebastian | Rami | Dante | Angel | Emily | Jacob | Rifat | all
| Low Level View favorite Medication Lost | 1 | 7 |  | 2022-04-02 |  | Rami
Low Levels - Sebastian | Low Level Add favorite medication | 2 | 7 |  | 2022-04-02
[8 empty] | 2022-03-24 | 4 | 6 | 4 | 1 | 3 | 2 | 6 | 26
Code- Emily | [7 empty] | 2022-03-25 | 5 | 6 | 4 | 2 | 4 | 4 | 7 | 32
| BRD Fixes Save Weight Goal | 3 | 6 |  | 2022-04-02 |  | Sebastian | 2022-03-26 | 6 | 6 | 6 | 2 | 6 | 4 | 6 | 36
| BRD Fixes Update Weight Goal | 4 | 6 |  | 2022-04-02 |  | Sebastian | 2022-03-27 | 6 | 6 | 4 | 10 | 4 | 4 | 5 | 39
[8 empty] | 2022-03-28 | 5 | 6 | 6 | 10 | 3 | 4 | 5 | 39
| View Record LL | 5 | 10 |  | 2022-04-02 |  | Angel | 2022-03-29 | 3 | 2 | 4 | 10 | 4 | 6 | 4 | 33
| Blob Store DAR | 6 | 5 |  | 2022-04-02 |  | Angel | 2022-03-30 | 6 | 4 | 6 | 8 | 5 | 6 | 5 | 40
| Fix Create Record LL | 7 | 3 |  | 2022-04-02 |  | Angel | 2022-03-31 | 7 | 3 | 4 | 8 | 4 | 6 | 4 | 36
| Create Record Backend Changes | 8 | 10 |  | 2022-04-02 |  | Angel | 2022-04-01 | 5 | 6 | 4 | 2 | 4 | 6 | 5 | 32
[8 empty] | 2022-04-02 | 6 | 5 | 4 | 2 | 6 | 6 | 4 | 33
| Finalize Search Health Location LL | 9 | 3 |  | 2022-04-02 |  | Jacob | Totals | 53 | 50 | 46 | 55 | 43 | 48 | 51 | 346
| Finalize View Health Location LL | 10 | 3 |  | 2022-04-02 |  | Jacob
| Code Search Health Locator Backend | 11 | 10 |  | 2022-04-02 |  | Jacob
| Code View Health Locator Backend | 12 | 10 |  | 2022-04-02 |  | Jacob
| Test favorite Medication | 13 | 5 |  | 2022-04-02 |  | Ramii
| LL view Reminder | 14 | 7 |  | 2022-04-02 |  | Dante
| LL Delete Reminder | 15 | 7 |  | 2022-04-02 |  | Dante
| LL Edit Reminder | 16 | 7 |  | 2022-04-02 |  | Dante
| Backend Code view reminder | 17 | 8 |  | 2022-04-02 |  | Dante
| LL Filter/Search Bar | 18 | 8 |  | 2022-04-02 |  | Rifat
| Filter/Search Bar Code | 19 | 9 |  | 2022-04-02 |  | Rifat
| BRD Fixes Search Diet Recommendation | 20 | 8 |  | 2022-04-02 |  | Emily
| BRD Fixes View Details Diet Recommendation | 21 | 8 |  | 2022-04-02 |  | Emily
124
2.9524