## Project Plan
Work Item | Task Name | Estimated Hours (Effort Points) | Planned Start Date | Planned End Date | Milestone 3 | Assigned | Free Time
Dar- Sebastian | DAR Report - Hosting Fixing | 3 |  | 2021-11-19 |  | Jacob |  | Sebastian | Rami | Dante | Angel | Emily | Jacob
| DAR Report - Database Fixing | 3 |  | 2021-11-19 |  | Rami | 2021-11-09 | 2 | 0 | 2 | 0 | 0 | 0
| DAR Report - Testing Fixing | 3 |  | 2021-11-19 |  | Angel | 2021-11-10 | 2 | 3 | 2 | 0 | 6 | 0
| DAR Report - API Medication Fixing | 2 |  | 2021-11-19 |  | Emily | 2021-11-11 | 5 | 3 | 4 | 2 | 6 | 4
| DAR Report- MAPS APIs Fixing | 2 |  | 2021-11-19 |  | Dante | 2021-11-12 | 5 | 6 | 2 | 4 | 5 | 4
| DAR Report - News API Fixing | 2 |  | 2021-11-19 |  | Sebastian | 2021-11-13 | 3 | 6 | 4 | 4 | 0 | 4
| DAR Report- Foods API Fixing | 2 |  | 2021-11-19 |  | Dante | 2021-11-14 | 6 | 6 | 4 | 8 | 5 | 0
| Milestone 1 Fixing SiteMap Reminders | 3 |  | 2021-11-19 |  | Sebastian | 2021-11-15 | 2 | 6 | 4 | 8 | 5 | 4
[7 empty] | 2021-11-16 | 3 | 6 | 4 | 8 | 5 | 4
[7 empty] | 2021-11-17 | 10 | 6 | 4 | 2 | 5 | 3
| Research for Low Level for Calorie Counter | 2 |  | 2021-11-16 |  | Rami | 2021-11-18 | 3 | 6 | 4 | 12 | 5 | 4
| Research for Low Level for Hot Topic | 2 |  | 2021-11-16 |  | Sebastian | 2021-11-19 | 3 | 6 | 4 | 4 | 4 | 4
| Research for Low Level for Medication lookup | 2 |  | 2021-11-16 |  | Rami | Totals | 44 | 54 | 38 | 52 | 46 | 31
| Research for Low Level for Health Locator | 2 |  | 2021-11-16 |  | Rami
| Research for Low Level for Reminders | 2 |  | 2021-11-16 |  | Sebastian
| Research for Low Level for Authentication | 2 |  | 2021-11-16 |  | Angel
| Research for Low Level for diet reccomendations | 2 |  | 2021-11-16 |  | Angel
| Research for Low Level for Track Records | 3 |  | 2021-11-16 |  | Sebastian
| Research for Low Level for make records | 3 |  | 2021-11-16 |  | Angel
Low Level- Rami | Low Level for Calorie Counter | 4 |  | 2021-11-19 |  | Rami
| Low Level for Hot Topic | 2 |  | 2021-11-19 |  | Sebastian
| Low Level for Medication lookup | 3 |  | 2021-11-19 |  | Rami
| Low Level for Health Locator | 3 |  | 2021-11-19 |  | Rami
| Low Level for Reminders | 3 |  | 2021-11-19 |  | Sebastian
| Low Level for Authentication | 3 |  | 2021-11-19 |  | Angel
| Low Level for diet reccomendations | 3 |  | 2021-11-19 |  | Angel
| Low Level for Track Records | 3 |  | 2021-11-19 |  | Sebastian
| Low Level for make records | 3 |  | 2021-11-19 |  | Angel
UM- Emily | User managment for Admins | 5 |  | 2021-11-19 |  | Emily
| User managment for Users | 5 |  | 2021-11-19 |  | Jacob
Logging-Dante | Idnentify key components to log | 6 |  | 2021-11-19 |  | Dante