## Project Plan
Task Name/Work Item | Estimated Hours (Effort Points) | Planned Start Date | Planned End Date | Milestone 3 | Assigned | Free Time
DAR Report - Authentication | 3 |  | 2021-11-04 |  | Sebastian Vasquez |  | Sebastian | Rami | Dante | Angel | Emily | Jacob
DAR Report - Hosting | 3 |  | 2021-11-04 |  | Jacob | 2021-10-30 | 0 | 0 | 2 | 0 | 0 | 0
DAR Report - Database | 3 |  | 2021-11-04 |  | Rami | 2021-10-31 | 0 | 3 | 2 | 0 | 3 | 0
DAR Report - Testing | 3 |  | 2021-11-04 |  | Angel | 2021-11-01 | 2 | 3 | 4 | 2 | 3 | 4
DAR Report - API Medication | 2 |  | 2021-11-04 |  | Emily | 2021-11-02 | 2 | 6 | 2 | 4 | 4 | 6
DAR Report- MAPS APIs | 2 |  | 2021-11-04 |  | Dante | 2021-11-03 | 4 | 6 | 2 | 4 | 0 | 4
DAR Report - News API | 2 |  | 2021-11-08 |  | Emily | 2021-11-04 | 4 | 6 | 4 | 8 | 5 | 4
DAR Report- Foods API | 2 |  | 2021-11-08 |  | Dante | 2021-11-05 | 7 | 6 | 4 | 8 | 5 | 6
DAR Report - Authentication Research | 3 |  | 2021-11-04 |  | Sebastian Vasquez | 2021-11-06 | 3 | 6 | 4 | 8 | 5 | 4
DAR Report - Hosting Research | 3 |  | 2021-11-04 |  | Jacob | 2021-11-07 | 10 | 6 | 3 | 2 | 5 | 3
DAR Report - Database Research | 3 |  | 2021-11-04 |  | Rami | 2021-11-08 | 3 | 6 | 4 | 12 | 7 | 2
DAR Report - Testing Research | 3 |  | 2021-11-04 |  | Angel | 2021-11-09 | 3 | 6 | 3 | 4 | 7 | 2
DAR Report - Medication Research | 3 |  | 2021-11-04 |  | Emily | Totals | 38 | 54 | 34 | 52 | 44 | 35
DAR Report- MAPS APIs Research | 3 |  | 2021-11-04 |  | Dante
DAR Report - News API Research | 3 |  | 2021-11-08 |  | Emily
DAR Report- Food API Research | 3 |  | 2021-11-08 |  | Dante
Research Low level design | 3 |  | 2021-11-10 |  | Rami
Research um | 3 |  | 2021-11-10 |  | Angel
Research logging | 3 |  | 2021-11-10 |  | Sebastian Vasquez