## Project Plan
Scrum Leader Sebastian Vasquez
| Task Name | Priority | Estimated Hours (Effort Points) | Planned Start Date | Planned End Date | Milestone 1 | Assigned | Free Time
[9 empty] | Sebastian | Rami | Dante | Angel | Emily | Jacob | all
[8 empty] | 2022-01-27 | 6 | 6.5 | 5 | 4 | 3 | 6 | 30.5
Low Levels - Sebastian | Switching from DES to JWT Token | 1 | 15 |  | 2022-02-07 |  | Sebastian Vasquez | 2022-01-28 | 2 | 4 | 4 | 5 | 7 | 4 | 26
Dar Reports - Rami | Organize Code | 2 | 7 |  | 2022-02-07 |  | Dante | 2022-01-29 | 6 | 3 | 4 | 5 | 8 | 0 | 26
Documents - Jacob | [7 empty] | 2022-01-30 | 5 | 4 | 4 | 5 | 7 | 3 | 28
| Fix Null Returns | 4 | 5 |  | 2022-02-07 |  | Dante | 2022-01-31 | 7 | 3 | 4 | 5 | 7 | 6 | 32
| Fix Naming Conventions of files | 5 | 3 |  | 2022-02-07 |  | Emily Sahyoun | 2022-02-01 | 2 | 3 | 4 | 5 | 4 | 6 | 24
[8 empty] | 2022-02-02 | 5 | 4 | 4 | 5 | 5 | 6 | 29
| Low Level Login | 6 | 15 |  | 2022-02-07 |  | Sebastian Vasquez | 2022-02-03 | 3 | 3 | 4 | 5 | 5 | 6 | 26
| Low Level Logout | 7 | 15 |  | 2022-02-07 |  | Jacob | 2022-02-04 | 3 | 4 | 4 | 5 | 5 | 4 | 25
| Low Level Account Recovery | 8 | 15 |  | 2022-02-07 |  | Angel | 2022-02-05 | 36 | 3 | 33 | 39 | 46 | 0 | 157
| Low Level Account Deletion | 9 | 15 |  | 2022-02-07 |  | Emily Sahyoun | 2022-02-06 |  | 4 |  |  |  | 3
| User Privacy Research | 10 | 5 |  | 2022-02-07 |  | Jacob | 2022-02-07 |  | 1.8 |  |  |  | 6
| Low Level Registration | 11 | 15 |  | 2022-02-07 |  | Rami | Totals | 75 | 43.3 | 70 | 83 | 97 | 50 | 403.5
| DAR Report - UI Testing | 12 | 6 |  | 2022-02-07 |  | Angel
| DAR Report - News API | 13 | 3 |  | 2022-02-07 |  | Rami
| DAR Report - Database | 14 | 3 |  | 2022-02-07 |  | Emily Sahyoun
| DAR Report - Zip | 15 | 6 |  | 2022-02-07 |  | Rami
| DAR Report - Frontend Framework | 16 | 6 |  | 2022-02-07 |  | Rami
| DAR Report - Maps API | 16 | 6 |  | 2022-02-07 |  | Sebastian
| Update Project Plan | 17 | 6 |  | 2022-02-07 |  | Jacob
146
19.1667