## Project Plan
Scrum Leader Sebastian Vasquez
Work Item | Task Name | Estimated Hours (Effort Points) | Planned Start Date | Planned End Date | Milestone 3 | Assigned | Free Time
Dar- Sebastian | DAR Report - Hosting Fixing | 4 |  | 2021-12-04 |  | Jacob |  | Sebastian | Rami | Dante | Angel | Emily | Jacob
| DAR Report - Database Fixing | 4 |  | 2021-12-04 |  | Sebastian | 2021-11-20 | 2 | 0 | 2 | 0 | 0 | 4
| DAR Report - Testing Fixing | 4 |  | 2021-12-04 |  | Angel | 2021-11-21 | 2 | 3 | 8 | 0 | 6 | 2
| DAR Report - API Medication Fixing | 4 |  | 2021-12-04 |  | Emily | 2021-11-22 | 5 | 3 | 8 | 2 | 6 | 8
| DAR Report- MAPS APIs Fixing | 4 |  | 2021-12-04 |  | Dante | 2021-11-23 | 5 | 6 | 8 | 4 | 5 | 4
| DAR Report - News API Fixing | 4 |  | 2021-12-04 |  | Sebastian | 2021-11-24 | 3 | 6 | 8 | 4 | 0 | 8
| DAR Report- Foods API Fixing | 4 |  | 2021-12-04 |  | Dante | 2021-11-25 | 6 | 6 | 8 | 8 | 5 | 4
| DAR Firewall | 7 |  | 2021-12-04 |  | Rami | 2021-11-26 | 2 | 6 | 4 | 8 | 5 | 4
| DAR Frontend Framework | 7 |  | 2021-12-04 |  | Sebastian | 2021-11-27 | 3 | 6 | 6 | 8 | 5 | 4
| DAR Unit Testing | 7 |  | 2021-12-04 |  | Angel | 2021-11-28 | 10 | 6 | 5 | 2 | 5 | 4
[7 empty] | 2021-11-29 | 3 | 6 | 5 | 12 | 5 | 4
Low Level- Rami | LL Logging Diagram | 5 |  | 2021-12-04 |  | Rami | 2021-11-30 | 3 | 6 | 5 | 4 | 4 | 4
| LL Logging Error Handinling | 3.5 |  | 2021-12-04 |  | Rami | 2021-12-01 | 3 | 6 | 5 | 12 | 5 | 4
| LL UML Logging | 4 |  | 2021-12-04 |  | Dante | 2021-12-02 | 3 | 6 | 5 | 4 | 4 | 4
| LL RS Logging | 2.5 |  | 2021-12-04 |  | Dante | 2021-12-03 | 3 | 6 | 5 | 12 | 5 | 4
| LL User Management | 5 |  | 2021-12-04 |  | Sebastian | 2021-12-04 | 3 | 6 | 5 | 4 | 4 | 4
| LL User Management Error handling | 3.5 |  | 2021-12-04 |  | Sebastian | Totals | 56 | 78 | 87 | 84 | 64 | 66
| LL UML User Management | 2 |  | 2021-12-04 |  | Emily
| Research DAO Code | 2 |  | 2021-12-04
Archiving-Jacob | Research Archiving Code | 2 |  | 2021-12-04 |  | Angel
UM- Emily | Research DAO Code | 2 |  | 2021-12-04 |  | Angel
| Research Manager Code | 2 |  | 2021-12-04 |  | Emily
| Research Service Level Code | 2 |  | 2021-12-04 |  | Angel
| Research Controller Level | 2 |  | 2021-12-04 |  | Angel
| Code DAO Level | 3 |  | 2021-12-04 |  | Sebastian
| Code Manager Level | 3 |  | 2021-12-04
| Code Service Level UM | 3 |  | 2021-12-04 |  | Angel
| Code Controller Level | 3 |  | 2021-12-04 |  | Angel
Logging-Dante | Code Service Level Logging | 3 |  | 2021-12-04 |  | Angel
Core Components- Angel | Changes to BRD | 8 |  | 2021-12-04 |  | Angel
| Changes to HL | 4 |  | 2021-12-04 |  | Rami
| Changes to Tech Spec | 2 |  | 2021-12-04 |  | Angel
| Changes to SiteMap | 4 |  | 2021-12-04 |  | Sebastian
| Changes to Network Diagram | 4 |  | 2021-12-04 |  | Jacob
| Changes to Project Plan | 6 |  | 2021-12-04 |  | Jacob
| Changes to Test Plan | 8 |  |  |  | Rami
| Set up MySQL Database | 9 |  |  |  | Sebastian
137.5