## Project Plan
Scrum Leader Sebastian Vasquez
| Task Name | Priority | Estimated Hours (Effort Points) | Planned Start Date | Planned End Date | Milestone 1 | Assigned | Free Time
[9 empty] | Sebastian | Rami | Dante | Angel | Emily | Jacob | Rifat | all
Low Levels - Sebastian | Switching from DES to JWT Token LL | 1 | 15 |  | 2022-02-07 |  | Sebastian Vasquez | 2022-02-08 | 2 | 6 | 4 | 8 | 7 | 6 | 7 | 40
Dar Reports - Rami | Organize Code | 2 | 7 |  | 2022-02-07 |  | Dante | 2022-02-09 | 6 | 6 | 4 | 5 | 8 | 3 | 5 | 37
Documents - Jacob | [7 empty] | 2022-02-10 | 5 | 6 | 4 | 8 | 7 | 6 | 2 | 38
[8 empty] | 2022-02-11 | 7 | 6 | 4 | 8 | 7 | 3 | 3 | 38
| Fix Naming Conventions of files | 2 | 5 |  | 2022-02-14 |  | Emily Sahyoun | 2022-02-12 | 2 | 3 | 4 | 0 | 4 | 6 | 5 | 24
[8 empty] | 2022-02-13 | 5 | 6 | 4 | 5 | 5 | 3 | 4 | 32
| Low Level Login Fix | 3 | 9 |  | 2022-02-14 |  | Sebastian Vasquez | 2022-02-14 | 3 | 6 | 4 | 2 | 5 | 8 | 5 | 33
| Low Level Logout FIx | 4 | 9 |  | 2022-02-14 |  | Jacob | 2022-02-15 | 7 | 6 | 4 | 8 | 6 | 6 | 4 | 41
| Low Level Account Recovery Fix | 5 | 9 |  | 2022-02-14 |  | Angel
| Low Level Account Deletion FIx | 6 | 9 |  | 2022-02-14 |  | Emily Sahyoun
| Low Level User Dashboard- track registration/login | 7 | 15 |  | 2022-02-14 |  | dante
| Low Level User Privacy | 8 | 15 |  | 2022-02-14 |  | Rifat
| Low Level Registration Fix | 9 | 9 |  | 2022-02-14 |  | Rami | Totals | 37 | 45 | 32 | 44 | 49 | 41 | 35 | 283
| DAR Report - UI Testing | 10 | 6 |  | 2022-02-14 |  | Angel
| DAR Report - News API | 11 | 3 |  | 2022-02-14 |  | Rami
| DAR Report - Zip | 12 | 4 |  | 2022-02-14 |  | Rifat
| DAR Report - Frontend Framework | 13 | 4 |  | 2022-02-14 |  | Rami
| DAR Report - Maps API | 14 | 4 |  | 2022-02-14 |  | Sebastian
| Fix UM LL | 15 | 15 |  | 2022-02-14 |  | Jacob
| Fix Logging LL | 16 | 7 |  | 2022-02-14 |  | Rami
| Fix Archiving LL | 17 | 11 |  | 2022-02-14 |  | Rifat
138
19.1667