## Project Plan
Scrum Leader Sebastian Vasquez
| Task Name | Priority | Estimated Hours (Effort Points) | Planned Start Date | Planned End Date | Milestone 1 | Assigned | Free Time
[9 empty] | Sebastian | Rami | Dante | Angel | Emily | Jacob | Rifat | all
Low Levels - Sebastian | Switching from DES to JWT Token Coding | 1 | 15 |  | 2022-02-25 |  | Sebastian Vasquez
Dar Reports - Rami | Organize Code | 2 | 7 |  | 2022-02-25 |  | Dante | 2022-02-16 | 6 | 6 | 4 | 5 | 8 | 3 | 6 | 38
Code- Emily | [7 empty] | 2022-02-17 | 5 | 6 | 4 | 8 | 7 | 6 | 4 | 40
[8 empty] | 2022-02-18 | 7 | 6 | 4 | 8 | 7 | 3 | 4 | 39
| Fix Naming Conventions of files | 3 | 5 |  | 2022-02-25 |  | Emily Sahyoun | 2022-02-19 | 2 | 3 | 4 | 0 | 4 | 6 | 9 | 28
[8 empty] | 2022-02-20 | 5 | 6 | 4 | 5 | 5 | 3 | 7 | 35
| Login Coding | 4 | 9 |  | 2022-02-25 |  | Sebastian Vasquez | 2022-02-21 | 3 | 6 | 4 | 2 | 5 | 8 | 5 | 33
| Logout Coding | 5 | 9 |  | 2022-02-25 |  | Jacob | 2022-02-22 | 7 | 6 | 4 | 8 | 6 | 6 | 6 | 43
| Account Recovery Coding | 6 | 9 |  | 2022-02-25 |  | Angel | 2022-02-23 | 7 | 6 | 4 | 8 | 6 | 6 | 5 | 42
| Account Deletion Coding | 7 | 9 |  | 2022-02-25 |  | Emily Sahyoun | 2022-02-24 | 7 | 6 | 4 | 8 | 6 | 6 | 2 | 39
| Low Level Login/Registration Tracker | 8 | 2 |  | 2022-02-25 |  | Dante | 2022-02-25 | 7 | 6 | 4 | 8 | 6 | 6 | 5 | 42
| Code Login/Registration tracker | 9 | 9 |  | 2022-02-25 |  | Dante | Totals | 56 | 57 | 40 | 60 | 60 | 53 | 53 | 379
| User Privacy Code | 10 | 9 |  | 2022-02-25 |  | Rifat
| User Privacy Low Level | 11 | 3 |  | 2022-02-25 |  | Rifat
| Registration Code | 12 | 9 |  | 2022-02-25 |  | Rami
| Registration Low Level Fix | 13 | 2 |  | 2022-02-25 |  | Rami
| Login Low Level Fix | 14 | 3 |  | 2022-02-25 |  | Sebastian
| Account Deletion Low Level Fix | 15 | 3 |  | 2022-02-25 |  | Emily Sahyoun
| DAR Report - UI Testing | 16 | 6 |  | 2022-02-25 |  | Angel
| DAR Report - News API | 17 | 3 |  | 2022-02-25 |  | Rifat
| DAR Report - Email Service | 18 | 4 |  | 2022-02-25 |  | Rifat
| DAR Report - Frontend Framework | 19 | 4 |  | 2022-02-25 |  | Rami
| DAR Report - Maps API | 20 | 4 |  | 2022-02-25 |  | Sebastian
| Fix UM LL | 21 | 15 |  | 2022-02-25 |  | Jacob
| Fix Logging LL | 22 | 7 |  | 2022-02-25 |  | Rami
| Fix Archiving LL | 23 | 11 |  | 2022-02-25 |  | Rifat
139
19.1667