## Project Plan
Scrum Leader Sebastian Vasquez
Work Item | Task Name | Priority | Estimated Hours (Effort Points) | Planned Start Date | Planned End Date | Milestone 3 | Assigned | Free Time
Dar- Rami | DAR Report - ORM | 1 | 4 |  | 2021-12-16 |  | Rami |  | Sebastian | Rami | Dante | Angel | Emily | Jacob | all
[8 empty] | 2021-12-06 | 2 | 0 | 2 | 0 | 0 | 4 | 8
Low Level- Rami | Low Level Create Account Fixing | 2 | 4 |  | 2021-12-16 |  | Sebastian Vasquez | 2021-12-07 | 2 | 3 | 3 | 0 | 6 | 4 | 18
| Low Level Create Account Error Cases Fixing | 3 | 4 |  | 2021-12-16 |  | Emily | 2021-12-08 | 3 | 3 | 3 | 0 | 6 | 4 | 19
| Low Level Update Account Fixing | 4 | 4 |  | 2021-12-16 |  | Emily | 2021-12-09 | 5 | 5 | 5 | 0 | 5 | 4 | 24
| Low Level Update Account Error Cases Fixing | 5 | 4 |  | 2021-12-16 |  | Jacob | 2021-12-10 | 4 | 7 | 3 | 5 | 4 | 8 | 31
| Low Level Enable/Disable Account Fixing | 6 | 4 |  | 2021-12-16 |  | Rami | 2021-12-11 | 6 | 6 | 5 | 8 | 5 | 4 | 34
| Low Level Enable/Disable Account Error Cases Fixing | 7 | 4 |  | 2021-12-16 |  | Rami | 2021-12-12 | 2 | 6 | 4 | 8 | 4 | 0 | 24
| Logging Fixes | 8 | 2 |  | 2021-12-16 |  | Dante | 2021-12-13 | 3 | 6 | 4 | 5 | 0 | 4 | 22
| Archiving Fixes | 9 | 2 |  | 2021-12-16 |  | Dante | 2021-12-14 | 4 | 0 | 4 | 5 | 4 | 4 | 21
[8 empty] | 2021-12-15 | 3 | 3 | 4 | 6 | 6 | 4 | 26
| Research Authorization | 10 | 3 |  | 2021-12-16 |  | Sebastian Vasquez | 2021-12-16 | 2 | 2 | 4 | 6 | 4 | 4 | 22
| Research Authentication | 11 | 3 |  | 2021-12-16 |  | Angel | 2021-12-17 | 3 | 4 | 4 | 6 | 5 | 4 | 26
| Coding Authorization (login/logut) | 12 | 6 |  | 2021-12-16 |  | Sebastian Vasquez | 2021-12-18 | 3 | 6 | 4 | 8 | 4 | 0 | 25
| Coding Authentication (access) | 13 | 6 |  | 2021-12-16 |  | Angel | Totals | 42 | 51 | 49 | 57 | 53 | 48 | 300
| Test Logging | 14 | 4 |  | 2021-12-16 |  | Dante
| Test Archiving | 15 | 4 |  | 2021-12-16 |  | Emily
| Test UM | 16 | 4 |  | 2021-12-16 |  | Rami
| Fixing DAL Levels | 17 | 6 |  | 2021-12-16 |  | Sebastian Vasquez
| Fixing Services | 18 | 3 |  | 2021-12-16 |  | Angel
Archiving-Jacob | Fixing Manager Level | 19 | 3 |  | 2021-12-16 |  | Emily
UM- Emily | Fixing Controller Level | 20 | 4 |  | 2021-12-16 |  | Dante
Logging-Dante | Coding Demo Project | 21 | 4 |  | 2021-12-16 |  | Dante
| Update Project Plan | 22 | 2 |  | 2021-12-16 |  | Jacob
| Fix Test Plan | 23 | 4 |  | 2021-12-16 |  | Jacob
| Fix Tech Spec | 24 | 2 |  | 2021-12-16 |  | Angel
90